## Sheet1
ID | SiteName | WMD | SiteType | FiscalYr | NumberNewWell(s) | WellType(s) | BriefStatus | Status | Lat_dd | Long_dd | My_Status
1 | Alston Bay | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.1804 | -82.0906 | C
2 | Alston New Cypress | SWF | Wetlands | 2017 | 1 | 1 SA | Complete | Completed | 28.2083 | -82.1031 | C
3 | Bay Lake | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | In Progress | Lance coordinating with Orange County Public schools to recon. | 28.4616 | -81.3754 | IP
4 | Big-Little Econ State forested - slough wetland | SJR | Wetlands | 2017 | 1 | 1 SA | Complete | Completed | 28.675 | -81.1258 | C
5 | Big-Little Econ State forested - small isolated | SJR | Wetlands | 2017 | 1 | 1 SA | Complete | Completed | 28.6908 | -81.1306 | C
6 | Bull Creek WMA-North Wetland | SJR | Wetlands | 2016 | 3 | 1 SA, 1 IA, 1 UFA | Complete | Completed | 28.1078 | -80.9786 | C
7 | Bull Creek WMA-South Wetland (SJ-JI) | SJR | Wetlands | 2016 | 3 | 1 SA, 1 IA, 1 UFA | Complete | Completed | 28.0139 | -80.9472 | C
8 | C-33 | SF | WL | 2018 - 2020 | 4 | 1 SA, 2 UFA, 1 LFA | Proposed |  | 28.1771 | -81.2329 | P
9 | Camp Lonesome | SF | Wetlands | 2017 | 1 | 1 SA | Proposed |  | 28.0564 | -81.1892 | P
10 | Campbell (Escape) Ranch | SJR | WL | 2016 | 1 | Core, 1 LFA | In Progress | core completion in FY2016; LFA planned FY18 | 27.829 | -80.9592 | IP
11 | City of Lakeland Wellfield G | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.1704 | -81.9028 | C
12 | City of Lakeland Wellfield J | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.1652 | -81.8883 | C
13 | City of Lakeland Wellfield K | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.161 | -81.8962 | C
14 | Clinch Lake | SWF | WL | 2018 - 2020 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with City of Frostproof | 27.7456 | -81.5356 | IP
15 | Coley Deep | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 27.7444 | -81.5295 | P
16 | Crooked Lake | SWF | WL | 2017 | 2 | 1 SA, 1 UFA, 1 Temp LFA II | In Progress | Coring and testing in progress | 27.8113 | -81.601 | IP
17 | Crooked Lake (Orange Co) | SJR | Wetlands | 2017 | 0 | N/A | In Progress | pending access | 28.5937 | -81.4774 | IP
18 | Crystal Lake | SWF | WL | 2018 - 2020 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with City of Lake Wales | 27.9035 | -81.5833 | IP
19 | Deseret Ranch/Lk Myrtle | SF | WL | 2017 | 4 | 1 UFA; 1 LFA, 1 SA; 1 IA | In Progress | WMD canal property, start of LFA in 2016; remaining wells and testing in FY17 | 28.3258 | -81.1687 | IP
20 | Dinner Lake | SWF | WL | 2017 | 1 | 1 SA | Proposed | Site acquisition is ongoing - location picked and negotiating with landowner. | 27.9679 | -81.6011 | P
21 | Dixie Lake (SJ-HO) - Lake Louisa State Park | SJR | Wetlands | 2017 | 1 | 1 SA | In Progress | site to be replaced with isolated wetland site with SA well with 6+ yrs gw data per Lance | 28.4381 | -81.7297 | P
22 | Duda-Whittle | SJR | WL | 2015 | 1 | Core, 1 LFA | Complete | Core completed Feb 2015; LFA in 2016 | 28.6888 | -81.7053 | C
23 | Eagle Lake | SWF | WL | 2017 | 2 | 1 SA, 1 UFA | In Progress | Site acquisition is ongoing - location picked and approved by City of Eagle Lake council, scheduled for May governing Board for approval | 27.9817 | -81.7596 | IP
24 | East Pine Island - Shingle Creek Basin | SF | Wetlands | 2016 | 2 | 2 SA, rainfall, wetlands survey | In Progress | Newly specified site | 28.3775 | -81.4503 | IP
25 | Econ Sandhills | SJR | WL | 2015 | 4 | 1SA, 1IA, 1UFA, 1LFA, Core | In Progress | Core, SA, IA, UFA completed July 2015; LFA proposed for 2017 | 28.591 | -81.166 | IP
26 | Fish Lake Deep NR Lakeland | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 28.0843 | -81.924 | P
27 | Frostproof | SWF | WL | 2017 | 2 | 1 SA, 1 UFA, 1 Temp LFA II | In Progress | Construction to start in Fall 2017 | 27.7304 | -81.59 | IP
28 | Green Swamp 4 | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.3919 | -81.9311 | C
29 | Green Swamp 7 | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.3128 | -81.9113 | C
30 | Green Swamp Bay | SWF | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.4218 | -81.9537 | C
31 | Groveland Sunshine Water Plant | SJR | WL | 2015 | 1 | 1UFA, Core | Complete | Core, UFA completed Mar 2015 | 28.6439 | -81.8025 | C
32 | Hal Scott Preserve - floodplain | SJR | Wetlands | 2017 | 1 | 1 SA | Proposed | site to be replaced with isolated wetland site with SA well with 6+ yrs gw data per Lance | 28.4817 | -81.1194 | P
33 | HH-2-IC | SF | WL | 2018 - 2020 | 4 | 1 SA, 2 UFA | Proposed |  | 28.2942 | -81.6014 | P
34 | Homeland Deep 9 | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 27.8117 | -81.8026 | P
35 | Intercession City | SF | Wetlands | 2016 | 1 | 1 SA | In Progress | Current WMD water level monitoring station; one new SA proposed | 28.2559 | -81.5041 | IP
36 | Intercession City - UFA monitoring start | SF | WL | 2018 - 2020 | 1 | 1 UFA | Proposed | Existing SA, IC, UFA and LFA wells on site | 28.2559 | -81.5041 | P
37 | Island Lake | SJR | Wetlands | 2017 | 0 | N/A | In Progress | FDOT approval granted; access needs to be formalized | 28.6961 | -81.3637 | IP
38 | Johns Lake - Scrub Point Preserve (Lake County) | SJR | Wetlands | 2017 | 3 | 1 SA, 1 UFA, 1 LFA | In Progress | current construction except LFA (out to bid); SA complete | 28.525 | -81.6799 | IP
39 | Keene's Pt Park | SF | Wetlands | 2017 | 1 | 1 SA | Proposed | Current monitoring agreement with Orange County needs updated | 28.4718 | -81.535 | P
40 | L-0199 | SJR | WL | 2018 - 2020 | 1 | 1 UFA | Complete | UFA repair; completed | 28.5653 | -81.6881 | C
41 | Lake Alfred Deep at Lake Alfred | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 28.0921 | -81.723 | P
42 | Lake Amoret | SWF | WL | 2017 | 2 | 1 SA, 1 UFA | In Progress | Construction is being scheduled | 27.8615 | -81.5697 | IP
43 | Lake Annie | SWF | WL | 2018 - 2020 | 2 | 1 SA, 1 UFA | Proposed | Moved to FY2017. Site re-scheduled from FY2015 due to site acquisition. Site acquisition is ongoing - no location picked yet. | 28.0001 | -81.6023 | P
44 | Lake Aurora | SWF | WL | 2017 | 2 | 1 SA, 1 UFA | Proposed | Site acquisition is ongoing - location picked and negotiating with land owner. | 27.8814 | -81.4672 | P
45 | Lake Bonnie | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed | MFL location | 27.9109 | -81.556 | P
46 | Lake Brantley | SJR | WL | 2018 - 2020 | 3 | 1 SA,1 IA, 1UFA | Proposed | MFL location | 28.6878 | -81.4284 | P
47 | Lake Easy | SWF | WL | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location in county park picked. Polk County has agreed to allow well. License agreement being prepared | 27.8556 | -81.5565 | IP
48 | Lake Eva | SWF | WL | 2018 - 2020 | 2 | 1 SA, 1 UFA | Proposed | Site acquisition is ongoing - location picked and negotiating with landowner - MFL location | 28.1007 | -81.627 | IP
49 | Lake Lee | SWF | WL | 2017 | 1 | 1 SA | Proposed | Real Estate has conducted initial field investigation for potential sites. | 27.9776 | -81.6085 | P
50 | Lake Louisa State Park (SJ-JB) | SJR | Wetlands | 2017 | 1 | 1 SA | In Progress | pending access | 28.4596 | -81.7411 | IP
51 | Lake Lowery | SWF | WL | 2018 - 2020 | 2 | 1 SA, 1 UFA | Proposed | MFL location | 28.1294 | -81.6903 | P
52 | Lake Mabel | SWF | WL | 2017 | 1 | 1 SA | Proposed | Site acquisition is ongoing - location picked and negotiating with land owner. | 27.9709 | -81.5935 | P
53 | Lake Marion Creek | SF | Wetlands | 2016 | 2 | 2 SA | In Progress | New station | 28.135 | -81.5517 | IP
54 | Lake McLeod | SWF | WL | 2017 | 1 | 1 SA | Proposed | Site acquisition is ongoing - evaluating two possible locations. | 27.9744 | -81.7537 | P
55 | Lake Prevatt-Wekiva Springs State Park | SJR | Wetlands | 2018 - 2020 | 0 | N/A | In Progress | met park manager, found acceptable sites, informal ok to go forward; moving forward with access. | 28.7091 | -81.4886 | IP
56 | Lake Proctor | SJR | Wetlands | 2016 | 1 | 1 SA | Complete | Completed | 28.7325 | -81.1014 | C
57 | Lake Starr | SWF | WL | 2017 | 2 | 1 SA, 1 UFA | Proposed | Site acquisition is ongoing - location picked and negotiating with land owner. | 27.9563 | -81.5926 | P
58 | Lake Sunset | SJR | Wetlands | 2016 | 0 | 1 UFA | Complete | Wetland monitoring transects completed. SA well has been constructed; a future UFA will be constructed by City of Mascotte after FY17 under their water use permit. | 28.5774 | -81.8895 | IP
59 | Lake Sylvan | SJR | Wetlands/MFL | 2016 | 0 | N/A | Complete | Completed | 28.8032 | -81.3821 | C
60 | Lake Trout | SWF | WL | 2018 - 2020 | 2 | 1 SA, 1 UFA | In Progress | Site acquisition is ongoing - location picked and approved by Governing Board | 27.6505 | -81.5072 | IP
61 | Lake Venus | SWF | WL | 2017 | 1 | 1 SA | Proposed | Site acquisition is ongoing - location picked and negotiating with land owner. | 27.9748 | -81.6096 | P
62 | Lake Wales (formerly Waverly) | SWF | WL | 2017 | 2 | 1 SA,1 UFA, 1 Temp LFA II | In Progress | Easements obtained. Construction to start Spring 2018 | 27.866 | -81.583 | IP
63 | Lake Wales Ridge State Forest Arbuckle 1 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.6872 | -81.4845 | IP
64 | Lake Wales Ridge State Forest Arbuckle 2 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.6873 | -81.4804 | IP
65 | Lake Wales Ridge State Forest Arbuckle 3 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.6966 | -81.4721 | IP
66 | Lake Wales Ridge State Forest Arbuckle 4 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.6616 | -81.4975 | IP
67 | Lake Wales Ridge Wildlife and Environmental Area Mountain Lake Cutoff 1 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.9194 | -81.6074 | IP
68 | Lake Wales Ridge Wildlife and Environmental Area Mountain Lake Cutoff 2 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.921 | -81.5964 | IP
69 | Lake Wales Ridge Wildlife and Environmental Area Mountain Lake Cutoff 3 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.9235 | -81.5965 | IP
70 | Lake Wales Ridge Wildlife and Environmental Area Mountain Lake Cutoff 4 | SWF | Wetlands | 2017 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with landowner | 27.9177 | -81.6014 | IP
71 | Long Branch | SJR | Wetlands | 2017 | 0 | N/A | In Progress | pending access | 28.5292 | -81.113 | IP
72 | LW4P | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 27.8434 | -81.8112 | P
73 | Minneola | SJR | WL | 2016 | 1 | 1 UFA, APT Testing | Complete | SA well on site, UFA well and APT completed | 28.6383 | -81.7256 | C
74 | N Boggy Marsh | SJR | Wetlands/MFL | 2017 | 2 | 1 SA, 1 UFA | In Progress | pending access; investigating existing UFA well alternative | 28.4088 | -81.7122 | IP
75 | North Lake Wales | SWF | WL | 2018 - 2020 | 1 | 1 SA | In Progress | Site acquisition is ongoing - location picked and negotiating with City of Lake Wales | 27.9108 | -81.5819 | IP
76 | North Osceola | SJR | WL | 2018 - 2020 | 3 | Core / 1 SA, 1 IA, 1 UFA | Proposed | Newy identified, close to CFWI boundary | 28.297 | -80.986 | P
77 | ORF-60 | SF | WL | 2018 - 2020 | 1 | 1 UFA | Proposed | Pairing UFA well with existing LFA | 28.3788 | -81.5877 | P
78 | OSF-52 | SF | WL | 2018 - 2020 | 1 | 1 LFA | In Progress | existing SA | 27.8031 | -81.1983 | IP
79 | OSF-53 - rehabilitation | SF | WL | 2016 | 3 | 1 UFA; 1 IA; 1 SA | In Progress | WMD property @ S-53 structure | 28.14 | -81.3506 | IP
80 | OSF-70 - St Cloud | SF | WL | 2018 - 2020 | 0 | Testing Only | Proposed | existing SA | 28.2524 | -81.3282 | P
81 | OUC - Air 19 | SF | WL | 2018 - 2020 | 1 | 1 UFA | Proposed | existing SA, LFA | 28.4033 | -81.3538 | P
82 | Pasture Reserve | SJR | WL | 2015 | 1 | 1 LFA | Complete | LFA completed Sept 2015 | 28.4811 | -81.8772 | C
83 | Peace River at Bartow | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 27.843 | -81.8113 | P
84 | Peace River at Fort Meade | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 27.7517 | -81.782 | P
85 | Pine Island /SJR | SJR | WL | 2016 | 2 | 1 SA, 1 UFA | Complete | Completed | 28.492 | -81.831 | C
86 | Praire Lake (SJ-GA) | SJR | Wetlands | 2017 | 0 | N/A | Complete | Wetland work complete; on-site SA well (CUP compliance) | 28.5983 | -81.511 | C
87 | Prince Parcel | SJR | WL | 2016 | 2 | 1 SA, 1 LFA | In Progress | LFA planned FY2018 | 27.6329 | -80.7652 | IP
88 | River Lakes Cons Area | SJR | WL | 2016 | 3 | 1SA, 1IA, 1UFA | Complete | Completed | 28.23 | -80.7956 | C
89 | Rock Springs Run "(Orange County Parks) - Spring Run" | SJR | Wetlands | 2017 | 1 | 1 SA | In Progress | pending access | 28.7554 | -81.4985 | IP
90 | Rock Springs Run State Preserve - forested strand | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | In Progress | replaces "seepage wetland" in work plan; moving forward with access; adjacent to existing SJR cluster | 28.7603 | -81.4692 | IP
91 | Rock Springs Run State Preserve - isolated forest | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | In Progress | met park manager, found acceptable sites, informal ok to go forward; moving forward with access. | 28.7772 | -81.446 | IP
92 | Rock Springs Run State Preserve - isolated marsh | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | In Progress | met park manager, found acceptable sites, informal ok to go forward; moving forward with access. | 28.7722 | -81.453 | IP
93 | ROMP 46 - Baird | SWF | WL | 2018 - 2020 | 4 | 1 SA, 2 UFA, 1 LFA, Coring/ Testing | In Progress |  | 27.7503 | -81.9665 | IP
94 | ROMP 73 - Winterhaven | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 28.0208 | -81.7312 | P
95 | ROMP 75 - Auburndale | SWF | WL | 2016 | 1 | 1 LFA II | Complete | Completed | 28.1089 | -81.8378 | C
96 | ROMP 87 - Green Swamp | SWF | WL | 2018 - 2020 | 1 | 1 SA | In Progress | District-owned, awaiting construction | 28.2202 | -82.0234 | IP
97 | ROMP 88 - Rock Ridge (Green Swamp West) | SWF | WL | 2017 | 2 | 1 UFA, 1 LFA I, 1 LFA II, Coring/ Testing | In Progress | Coring and testing to about 2,650 feet bls began 11/2016 and is expected to take a year to complete. Well construction is expected to take a year to complete after coring and testing. Well construction costs are in FY2017 budget. | 28.3107 | -81.9114 | IP
98 | ROMP 88.5 - Northeast Polk (formerly Green Swamp East) | SWF | WL | 2018 - 2020 | 4 | 1 SA, 1 UFA, 1 LFA I, 1 LFA II, Coring/Testing | Proposed | Location still under review | 28.291 | -81.772 | P
99 | Round Lake | SJR | Wetlands | 2017 | 0 | wetland only | Complete | new site added 2017 | 28.7787 | -81.5957 | IP
100 | S.R. 60 near Lake Weo & Rosilie | SF | WL | 2018 - 2020 | 4 | 1 SA, 1 UFA, 2 LFA | Proposed |  | 27.8753 | -81.4004 | P
101 | Sanlon Ranch | SWF | WL | 2018 - 2020 | 1 | 1 SA | Proposed |  | 28.0002 | -81.923 | P
102 | Thornhill Deep Near Davenport | SWF | WL | 2017 | 2 | 1 SA, 1 UFA | Proposed | Site acquisition is ongoing - easement and agreement language updated and Upland Easement app for State Lands almost complete. Not pursuing LFA wells at this time but adding an UFA APT. | 28.2141 | -81.6589 | P
103 | Tosohatchee WMA - isolated marsh | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | Proposed | new site: will need SA well, recon, and access agreement | 28.5153 | -80.993 | P
104 | Tosohatchee WMA - large isolated forested wetland | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | Proposed | new site: will need SA well, recon, and access agreement | 28.4959 | -80.9618 | P
105 | Wekiva River Swamp-Wekvia Springs State Park | SJR | Wetlands | 2018 - 2020 | 1 | 1 SA | In Progress | met park manager, found acceptable sites, informal ok to go forward; moving forward with access. | 28.7137 | -81.466 | IP
106 | West of Lake Jessup | SJR | WL | 2017 | 4 | Core / SA, IA, UFA, LFA | In Progress | pending access | 28.785 | -81.242 | IP
107 | Wolf Creek Ranch CA | SJR | WL | 2018 - 2020 | 4 | Core / 1 SA, 1 IA, 1 UFA, 1 LFA | Proposed | on conservation easement; will look at alternative sites | 27.893 | -80.861 | P
108 | World Gateway | SF | Wetlands | 2016 | 1 | 1 SA | In Progress | Current WMD water level monitoring station, stilling well proposed. | 28.3535 | -81.5039 | IP
109 | Yeehaw Junction | SJR | WL | 2017 | 4 | Core / SA, IA, UFA, LFA | In Progress | Targeted for FY 2017 construction; LFA removed | 27.707 | -80.907 | IP